## 00_Control_Tower
EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower | EnergyIQ Product & Delivery Control Tower
Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm | Management draft · verified against main@7070843 and GitHub Issues on 17 Aug 2026 · dates are indicative until owners confirm
CAPABILITIES |  | ENGINEERING VERIFIED |  | IN VALIDATION |  | IN PROGRESS |  | PLANNED / DISCOVERY |  | OPEN DECISIONS |  | OVERALL RAG |  | STATUS BASIS
20 |  | 6 |  | 7 |  | 1 |  | 6 |  | 3 |  | AMBER |  | Engineering evidence strong; customer acceptance and cross-project repeatability remain the release gate.
CURRENT MANAGEMENT CONCLUSION | [8 empty] | NEXT THREE GATES
EnergyIQ has moved beyond a static dashboard: the trusted data foundation, project-specific Overviews, AI Analyst and Preschool Layer 1–3/A→B are engineered. The next value gate is human acceptance, Ngee Ann repeatability and a feedback loop that turns useful Insights into reusable Methods/SOPs. | [8 empty] | G1 | Customer acceptance | Charles + Ngee accounts complete critical journeys
[9 empty] | G2 | Cross-project repeatability | Ngee Layer 1–3 and A/B pass without stale Artifacts
[9 empty] | G3 | Learning loop | One useful Insight becomes an approved reusable Method
DELIVERY HEALTH BY WORKSTREAM
Workstream | Deliverables | Verified | In validation / progress | Avg complete | RAG |  | Decision / risk | Owner | Due | Status | Mitigation / decision
Verified Foundation | 5 | 5 | 0 | 100% | Green |  | Management reporting can under- or over-state progress | Product | 2026-08-21 | Open | Reconcile each capability with current main, issue and acceptance evidence
Acceptance Hardening | 6 | 0 | 6 | 77.5% | Amber |  | Product may appear complete but fail real review | Product + QA | 2026-08-24 | Open | Run named-account browser journeys and record evidence
Cross-project AI | 3 | 0 | 1 | 40% | Amber |  | Platform becomes project-specific and expensive to scale | Architecture | 2026-08-28 | Open | Share lifecycle and identity; keep project Packs and questions separate
Learning Loop | 3 | 0 | 0 | 10% | Green |  | Protects the shortest route to customer proof | Sponsor | 2026-08-21 | Open | Recommend Ngee + A/B + feedback loop first
Pilot Scale | 4 | 0 | 0 | 11.25% | Green |  | Without owners dates remain indicative | Sponsor | 2026-08-21 | Open | Publish RACI for R1-R2

## 01_Capability_Register
EnergyIQ Capability Register | EnergyIQ Capability Register | EnergyIQ Capability Register | EnergyIQ Capability Register | EnergyIQ Capability Register | EnergyIQ Capability Register | EnergyIQ Capability Register | EnergyIQ Capability Register | EnergyIQ Capability Register
One row per product capability · status is evidence-based, not feature-count based | One row per product capability · status is evidence-based, not feature-count based | One row per product capability · status is evidence-based, not feature-count based | One row per product capability · status is evidence-based, not feature-count based | One row per product capability · status is evidence-based, not feature-count based | One row per product capability · status is evidence-based, not feature-count based | One row per product capability · status is evidence-based, not feature-count based | One row per product capability · status is evidence-based, not feature-count based | One row per product capability · status is evidence-based, not feature-count based
ID | Layer / Workstream | Capability | Project / Surface | Customer outcome | Status | % Complete | Evidence basis | Evidence URL / Reference
CAP-01 | Data Foundation | Project-scoped Snapshot and Evidence boundary | All projects | Trusted facts can be rerun and audited | Engineering Verified | 100% | Published Snapshot, exact Scope/Period and Evidence Catalog | https://github.com/Zion74/energyiq-datafoundry/issues/25
CAP-02 | Deterministic Overview | Ngee Ann project-specific Overview foundation | Ngee Ann | FM can see levels, circuits, time behaviour and priorities | Engineering Verified | 100% | Golden slice and deterministic projections | https://github.com/Zion74/energyiq-datafoundry/issues/6
CAP-03 | Deterministic Overview | Preschool portfolio decision Overview | Preschool | Management can compare centres and operating behaviour | Engineering Verified | 100% | Benchmark, distribution and operating analysis | https://github.com/Zion74/energyiq-datafoundry/issues/10
CAP-04 | AI Analyst | Trusted natural-language analysis with scoped Evidence | All projects | Users can investigate questions beyond the template | Engineering Verified | 100% | Scoped query, Evidence and Saved Analysis | https://github.com/Zion74/energyiq-datafoundry/issues/14
CAP-05 | AI Layer 1 | Cross-section Key Findings | Preschool | Boss can understand the priority conclusions quickly | Acceptance Pending | 90% | Server-persisted Executive Artifact; content review remains | https://github.com/Zion74/energyiq-datafoundry/issues/47
CAP-06 | AI Layer 2 | Section Interpretation and Insight Cards | Preschool | Each section explains what matters and opens deeper questions | Acceptance Pending | 90% | Independent section Artifacts and saved restore | https://github.com/Zion74/energyiq-datafoundry/issues/47
CAP-07 | AI Layer 3 | Additional AI Insights and governed publication | Preschool | New angles can be reviewed and published without replacing facts | Acceptance Pending | 90% | Provider pass@3 and approved-candidate publication | https://github.com/Zion74/energyiq-datafoundry/issues/58
CAP-08 | Continuous Analysis | Preschool Snapshot A to B rerun | Preschool | Users can see retained, updated, new and removed conclusions | Engineering Verified | 100% | Real A/B technical acceptance completed | https://github.com/Zion74/energyiq-datafoundry/issues/60
CAP-09 | Admin | Project Overview and AI readiness | All projects | Admins can see what is missing and generate deliberately | Engineering Verified | 100% | Readiness and Generate Missing analysis flows | https://github.com/Zion74/energyiq-datafoundry/issues/49
CAP-10 | Access | Multi-account and project-boundary acceptance | Preschool + Ngee Ann | Charles sees all projects; customer accounts see only theirs | Acceptance Pending | 70% | Human/browser acceptance remains | https://github.com/Zion74/energyiq-datafoundry/issues/53
CAP-11 | AI Platform | Ngee Ann server-persisted Layer 1-3 Adapter | Ngee Ann | Ngee uses the common AI lifecycle without copying Preschool | In Progress | 85% | Implementation on main; issue remains open | https://github.com/Zion74/energyiq-datafoundry/issues/55
CAP-12 | Continuous Analysis | Ngee Ann Snapshot A to B value acceptance | Ngee Ann | New data updates Overview and AI conclusions safely | Planned | 15% | Depends on CAP-11 acceptance | https://github.com/Zion74/energyiq-datafoundry/issues/56
CAP-13 | Learning Loop | Insight usefulness feedback to Method/SOP | All projects | Useful analysis angles become reusable organisational know-how | Planned | 10% | Feedback and governance ticket ready | https://github.com/Zion74/energyiq-datafoundry/issues/57
CAP-14 | AI Operations | Exact Finding, Skill, Method and Tool trace | Admin | Admins can understand how a conclusion was produced | Acceptance Pending | 70% | Ready for human review | https://github.com/Zion74/energyiq-datafoundry/issues/61
CAP-15 | Harness Configuration | Project Harness configuration read model and Admin UI | Admin | Admins can inspect available and actually-used capabilities | Acceptance Pending | 65% | Human acceptance across HCFG-1/2 and AIOPS-1 | https://github.com/Zion74/energyiq-datafoundry/issues/62
CAP-16 | Harness Governance | Governed Project Harness Policy revisions | Admin | Changes to model, tools and skills become reviewable revisions | Planned | 10% | Policy revision ticket open | https://github.com/Zion74/energyiq-datafoundry/issues/66
CAP-17 | Template Evolution | AI Template Change Proposal, Diff and Preview | Admin | AI can propose software changes without auto-publishing | Planned | 20% | Approval-gated proposal flow | https://github.com/Zion74/energyiq-datafoundry/issues/46
CAP-18 | Visual Analysis | Controlled AI charts and visual canvas | All projects | Complex insights can use charts when they materially help | Planned | 10% | Controlled chart and Finding canvas backlog | https://github.com/Zion74/energyiq-datafoundry/issues/35
CAP-19 | Pilot Operations | Customer acceptance, runbook and release readiness | Preschool + Ngee Ann | The platform can be handed to real pilot users safely | Acceptance Pending | 55% | Pilot release and customer acceptance remain open | https://github.com/Zion74/energyiq-datafoundry/issues/21
CAP-20 | Coding Agent | User request to repeatable software capability | Future | Customer-specific analysis can become governed product code | Discovery | 5% | Architecture and isolation discovery; not a current commitment | Product roadmap hypothesis

## 02_Delivery_Plan
EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan | EnergyIQ Delivery Plan
90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower | 90-day execution sequence · editable status and progress feed the Control Tower
ID | Workstream | Capability ID | Deliverable | Status | % Complete | Owner | Start | Due | Dependency | Acceptance / Exit Gate | Evidence URL | Next Action | RAG
DLV-001 | Verified Foundation | CAP-01 | Lock Snapshot, Evidence and project-scoped identity | Engineering Verified | 100% | Platform | 2026-08-03 | 2026-08-07 |  | Exact identity tests and persisted Evidence | https://github.com/Zion74/energyiq-datafoundry/issues/25 | Keep regression suite green | Green
DLV-002 | Verified Foundation | CAP-02 | Deliver Ngee Ann deterministic Overview | Engineering Verified | 100% | Product + Data | 2026-08-03 | 2026-08-10 | DLV-001 | Golden data, hierarchy and decision-page evidence | https://github.com/Zion74/energyiq-datafoundry/issues/6 | Use as the non-AI truth layer | Green
DLV-003 | Verified Foundation | CAP-03 | Deliver Preschool deterministic decision Overview | Engineering Verified | 100% | Product + Data | 2026-08-06 | 2026-08-12 | DLV-001 | Benchmark and operating sections accepted in engineering | https://github.com/Zion74/energyiq-datafoundry/issues/10 | Continue human content review | Green
DLV-004 | Verified Foundation | CAP-04 | Connect trusted AI Analyst and Saved Analysis | Engineering Verified | 100% | AI Platform | 2026-08-03 | 2026-08-07 | DLV-001 | Scoped queries, Evidence and restore tests | https://github.com/Zion74/energyiq-datafoundry/issues/14 | Maintain project and period boundaries | Green
DLV-005 | Verified Foundation | CAP-08 | Complete Preschool A to B engineering acceptance | Engineering Verified | 100% | Product + AI | 2026-08-14 | 2026-08-17 | DLV-003;DLV-004 | Overview and AI domain change; stale Artifact rejected | https://github.com/Zion74/energyiq-datafoundry/issues/60 | Repeat on Ngee after adapter acceptance | Green
DLV-101 | Acceptance Hardening | CAP-05 | Human-review Preschool Key Findings | Acceptance Pending | 90% | Product | 2026-08-17 | 2026-08-21 | DLV-003 | Boss can identify top conclusions in 20 seconds | https://github.com/Zion74/energyiq-datafoundry/issues/47 | Score clarity, priority and usefulness | Amber
DLV-102 | Acceptance Hardening | CAP-06 | Human-review every Preschool Section Insight | Acceptance Pending | 90% | Product + Energy | 2026-08-17 | 2026-08-24 | DLV-003 | Summary is direct; Insights add a worthwhile angle | https://github.com/Zion74/energyiq-datafoundry/issues/47 | Record weak/redundant outputs | Amber
DLV-103 | Acceptance Hardening | CAP-07 | Approve and publish useful Additional Insights | Acceptance Pending | 90% | Energy + AI | 2026-08-17 | 2026-08-24 | DLV-004 | Fact, inference and speculation remain honestly separated | https://github.com/Zion74/energyiq-datafoundry/issues/58 | Review current production candidates | Amber
DLV-104 | Acceptance Hardening | CAP-10 | Run Charles and Ngee multi-account browser acceptance | Acceptance Pending | 70% | QA + Ops | 2026-08-17 | 2026-08-24 | DLV-002;DLV-003 | Admin sees all; Ngee account sees Ngee only; AI works | https://github.com/Zion74/energyiq-datafoundry/issues/53 | Capture screenshots and access matrix | Amber
DLV-105 | Acceptance Hardening | CAP-14 | Accept Admin AI Operations and Finding trace | Acceptance Pending | 70% | Admin Product | 2026-08-17 | 2026-08-28 | CAP-09 | Available vs used is clear; no GET triggers Provider | https://github.com/Zion74/energyiq-datafoundry/issues/61 | Complete human review | Amber
DLV-106 | Acceptance Hardening | CAP-19 | Publish pilot runbook and rollback evidence | In Progress | 55% | Ops | 2026-08-20 | 2026-08-28 | DLV-104 | Health, backup, rollback and account runbook accepted | https://github.com/Zion74/energyiq-datafoundry/issues/21 | Name operations owner | Amber
DLV-201 | Cross-project AI | CAP-11 | Close Ngee Ann server-persisted Layer 1-3 Adapter | In Progress | 85% | AI Platform | 2026-08-15 | 2026-08-28 | DLV-002;DLV-004 | Saved/live restore exact; normal page open starts zero Provider runs | https://github.com/Zion74/energyiq-datafoundry/issues/55 | Finish Provider and human acceptance | Amber
DLV-202 | Cross-project AI | CAP-12 | Run real Ngee Ann Snapshot A to B | Planned | 15% | Product + AI | 2026-08-31 | 2026-09-11 | DLV-201 | Retained, updated, new and removed conclusions are visible | https://github.com/Zion74/energyiq-datafoundry/issues/56 | Prepare controlled Snapshot B | Blue
DLV-203 | Cross-project AI | CAP-11 | Document common adapter and project-specific pack boundary | Planned | 20% | Architecture | 2026-09-07 | 2026-09-18 | DLV-201;DLV-202 | A third project can implement the contract without copying sections | https://github.com/Zion74/energyiq-datafoundry/issues/54 | Extract only proven common mechanisms | Blue
DLV-301 | Learning Loop | CAP-13 | Capture usefulness, novelty, clarity and Explore events | Planned | 10% | Product Analytics | 2026-09-21 | 2026-10-02 | DLV-102;DLV-202 | Feedback is project/snapshot/finding scoped | https://github.com/Zion74/energyiq-datafoundry/issues/57 | Define minimal feedback contract | Blue
DLV-302 | Learning Loop | CAP-13 | Create Insight-to-Method proposal flow | Planned | 10% | Energy + Admin | 2026-09-28 | 2026-10-09 | DLV-301 | User-approved Insight can become a reviewable Method proposal | https://github.com/Zion74/energyiq-datafoundry/issues/57 | Define proposal and approval UI | Blue
DLV-303 | Learning Loop | CAP-16 | Version governed Harness policy | Planned | 10% | AI Platform | 2026-09-28 | 2026-10-09 | DLV-105 | Policy revisions are attributable and recoverable | https://github.com/Zion74/energyiq-datafoundry/issues/66 | Agree governance owner | Blue
DLV-401 | Pilot Scale | CAP-17 | Prototype AI Template Proposal, Diff and Preview | Planned | 20% | Admin Product | 2026-10-12 | 2026-10-23 | DLV-203;DLV-303 | AI proposes; human reviews; publish remains explicit | https://github.com/Zion74/energyiq-datafoundry/issues/46 | Keep production publish approval-gated | Blue
DLV-402 | Pilot Scale | CAP-18 | Prototype controlled visual Insight canvas | Planned | 10% | Frontend + AI | 2026-10-19 | 2026-10-30 | DLV-301 | Charts appear only when they improve understanding | https://github.com/Zion74/energyiq-datafoundry/issues/35 | Select two high-value chart patterns | Blue
DLV-403 | Pilot Scale | CAP-20 | Run isolated Coding Agent architecture spike | Discovery | 5% | Architecture | 2026-10-19 | 2026-11-06 | DLV-203;DLV-303 | One user request becomes a reviewable, rerunnable proposal | Product roadmap hypothesis | Keep outside production runtime | Blue
DLV-404 | Pilot Scale | CAP-19 | Complete customer handover and commercial pilot review | Planned | 10% | Product + Sales | 2026-11-02 | 2026-11-06 | DLV-104;DLV-202;DLV-302 | Usage, value, support and next-phase decisions are signed | https://github.com/Zion74/energyiq-datafoundry/issues/21 | Agree pilot owner and success metrics | Blue

## 03_Roadmap
EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026 | EnergyIQ Product Roadmap · Aug–Nov 2026
Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed | Outcome-based phases and exit gates · dates are indicative until R1 owners and access are confirmed
Phase | Stage | Start | End | Objective | Capability bundle | Exit Gate | Commitment | Status | Business value
R0 | Verified Foundation | 2026-08-03 | 2026-08-17 | Trusted data, deterministic Overviews and Preschool Layer 1-3 | Snapshot/Evidence, two project renderers, AI Analyst, Preschool A/B | Engineering evidence exists; customer acceptance is separate | Completed engineering baseline | Engineering Verified | Prove the product is more than a static dashboard
R1 | Acceptance Hardening | 2026-08-17 | 2026-08-28 | Make the current product safe for Charles and Ngee reviewers | Content quality, visual hierarchy, accounts, Admin traces, runbook | Named users complete critical journeys with captured evidence | Committed after owner confirmation | In Progress | Convert engineering output into customer trust
R2 | Cross-project AI | 2026-08-31 | 2026-09-18 | Prove the AI lifecycle generalises beyond Preschool | Ngee Layer 1-3 Adapter, real Provider, Saved restore, Ngee A/B | Ngee normal open starts zero Provider; A/B changes honestly | Conditional on R1 and Snapshot B | Planned | Show repeatability across different project structures
R3 | Learning Loop | 2026-09-21 | 2026-10-09 | Turn useful Insights into reusable Methods and SOPs | Usefulness events, Method proposals, approval, Harness policy | At least one Insight becomes an approved reusable method | Conditional on real customer feedback | Planned | Create a compounding expert-knowledge advantage
R4 | Pilot Scale | 2026-10-12 | 2026-11-06 | Prepare productisation and the next controlled capability frontier | Template proposals, visual canvas, Coding Agent spike, handover | Pilot metrics and next release are approved; no autonomous publish | Indicative, not a customer commitment | Discovery | Move from bespoke delivery to repeatable product growth
TIMELINE VIEW
Phase | 17 Aug | 31 Aug | 21 Sep | 12 Oct | 2 Nov
R1 Acceptance | ●
R2 Cross-project AI |  | ●
R3 Learning Loop |  |  | ●
R4 Pilot Scale |  |  |  | ● | ●

## 04_Product_Map
EnergyIQ Product Map | EnergyIQ Product Map | EnergyIQ Product Map | EnergyIQ Product Map | EnergyIQ Product Map | EnergyIQ Product Map
The product turns trusted utility data into decisions, deeper analysis and reusable expert methods | The product turns trusted utility data into decisions, deeper analysis and reusable expert methods | The product turns trusted utility data into decisions, deeper analysis and reusable expert methods | The product turns trusted utility data into decisions, deeper analysis and reusable expert methods | The product turns trusted utility data into decisions, deeper analysis and reusable expert methods | The product turns trusted utility data into decisions, deeper analysis and reusable expert methods
Step | Layer | Input | What the product does | Customer-facing output | Value
1 | Data Foundation | Excel / Tuya / Meter data | Normalize, validate and bind exact time/scope | Snapshot + Evidence Catalog | Trusted facts
2 | Deterministic Experience | Published Snapshot | Render project-specific metrics, charts and alerts | Overview + Explorer | See and verify
3 | AI Layer 1 | Accepted Section Artifacts | Synthesize cross-section priorities | Key Findings | Understand quickly
4 | AI Layer 2 | Section Pack + Evidence | Explain patterns and worthwhile angles | Section Interpretation | Think more deeply
5 | AI Layer 3 | Cross-section facts + Methods | Discover additional hypotheses, alerts and SOP angles | Additional AI Insights | Discover the non-obvious
6 | AI Analyst | Selected Finding + exact project context | Query, compare, test and build a decision narrative | Analysis + report | Investigate and decide
7 | Learning Loop | User feedback + approved Insights | Propose, review and publish reusable Methods/SOPs | Method Library | Reuse expertise
8 | Coding Agent | Approved user requirement | Generate reviewable software/template proposals | Rerunnable capability | Scale customisation
X | Cross-cutting Control Plane | Workspace, Project, model, tools and policies | Identity, access, Run trace, Artifact restore and approval | Admin Harness + AI Operations | Trust and governance

## 05_Technical_Architecture
EnergyIQ Technical Architecture | EnergyIQ Technical Architecture | EnergyIQ Technical Architecture | EnergyIQ Technical Architecture
Actual target architecture: project-specific expression over a shared trusted data and governed AI control plane | Actual target architecture: project-specific expression over a shared trusted data and governed AI control plane | Actual target architecture: project-specific expression over a shared trusted data and governed AI control plane | Actual target architecture: project-specific expression over a shared trusted data and governed AI control plane
Layer | Components | Responsibility / Boundary | Primary owner
Experience | Overview; Project Explorer; AI Analyst; Admin; Reports | Role-scoped decisions, drill-down and governance | Customer / Admin
Project Product | Renderer Registry; Project Recipe; Template Release; A/B Change Summary | Project-specific expression without hard-coded platform forks | Product
Governed AI | Key Findings; Section Interpretation; Additional Insights; AI Analysis | Facts, inference and speculative angles remain distinguishable | AI Platform + Energy
Harness | Model Profile; Skill; Method; Tool; Context policy; Run Finalizer | Server-owned capability boundary and reproducible execution | AI Platform
Analysis Contracts | Section Pack; Analysis Pack; Evidence Catalog; Read Models | Complete project facts and explicit missing evidence | Data + Domain
Data Foundation | Import Batch; Raw Reading; Interval Fact; Metric/Rule revisions; Snapshot | Deterministic, traceable utility facts | Data
Persistence | Metadata; Artifact Store; Saved Analysis; Run/Event trace | Exact identity, restore, audit and A/B isolation | Platform
Cross-cutting | Workspace/Project isolation; auth; secrets; observability; backup | Multi-tenant safety and operability | Platform + Ops

## 06_Business_Route
EnergyIQ Business Route | EnergyIQ Business Route | EnergyIQ Business Route | EnergyIQ Business Route | EnergyIQ Business Route | EnergyIQ Business Route | EnergyIQ Business Route
Commercial hypothesis for validation · not yet an approved price list or customer commitment | Commercial hypothesis for validation · not yet an approved price list or customer commitment | Commercial hypothesis for validation · not yet an approved price list or customer commitment | Commercial hypothesis for validation · not yet an approved price list or customer commitment | Commercial hypothesis for validation · not yet an approved price list or customer commitment | Commercial hypothesis for validation · not yet an approved price list or customer commitment | Commercial hypothesis for validation · not yet an approved price list or customer commitment
Stage | Offer | Buyer / User | Customer pain | EnergyIQ delivery | Proof of value | Commercial hypothesis
1 | Diagnostic Demo | FM / Energy manager | Data exists but priorities are unclear | One project Snapshot, Overview and 3-5 decision findings | User agrees the findings are worth investigating | Fixed-scope paid assessment
2 | Pilot | Facilities team + Sponsor | Analysis is manual and difficult to repeat | Overview, Layer 1-3, AI Analyst, accounts and A/B | Repeated use across two data updates | Project subscription + onboarding
3 | Multi-project Rollout | Portfolio owner | Different sites need consistent governance but different analysis | Shared platform plus project-specific Packs/Renderers | Additional projects onboard without platform fork | Per-project / portfolio subscription
4 | Expert Intelligence | Energy consultant / sophisticated FM | High-value know-how is trapped in individuals | Method/SOP Library, feedback and governed publication | Useful Methods recur across projects | Professional intelligence add-on
5 | Enterprise | Large owner / partner | Governance, traceability and integrations become critical | Admin Harness, AI Operations, policy revisions and APIs | Audit and operating requirements accepted | Enterprise plan and services
SELLING STORY
1 | Start with real customer data |  | Show a trusted diagnostic, not a generic AI demo
2 | Prove repeatability |  | Use A→B to show the product changes when the data changes
3 | Expand across projects |  | Reuse the platform while preserving project-specific Packs and Renderers
4 | Compound expertise |  | Turn useful Insights into approved Methods/SOPs

## 07_RAID_Decisions
RAID & Decision Log | RAID & Decision Log | RAID & Decision Log | RAID & Decision Log | RAID & Decision Log | RAID & Decision Log | RAID & Decision Log | RAID & Decision Log | RAID & Decision Log | RAID & Decision Log | RAID & Decision Log
Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger | Every risk, assumption and decision has an owner, due date, action and escalation trigger
ID | Type | Area | Description | Impact | Severity | Owner | Due | Status | Mitigation / Decision | Escalation Trigger
R-01 | Risk | Status truth | GitHub parent issues and implementation commits can drift | Management reporting can under- or over-state progress | High | Product | 2026-08-21 | Open | Reconcile each capability with current main, issue and acceptance evidence | Any slide claims Done without linked evidence
R-02 | Risk | Customer acceptance | Engineering tests do not prove Charles/Ngee usability | Product may appear complete but fail real review | Critical | Product + QA | 2026-08-24 | Open | Run named-account browser journeys and record evidence | Acceptance #53 remains open past R1
R-03 | Risk | Ngee generalisation | Ngee may accidentally copy Preschool contracts | Platform becomes project-specific and expensive to scale | High | Architecture | 2026-08-28 | Open | Share lifecycle and identity; keep project Packs and questions separate | Preschool section IDs appear in Ngee artifacts
R-04 | Risk | AI value | Overly strict Evidence rules produce bland output; loose rules overclaim | Users lose trust or see no new value | High | Energy + AI | 2026-09-04 | Open | Separate observations, inference and speculative angles; human score usefulness | Speculation displayed as confirmed fact
R-05 | Risk | Artifact freshness | Old AI output could be shown after Snapshot changes | A/B becomes misleading | Critical | AI Platform | 2026-09-11 | Open | Exact Snapshot/Release/Period identity and no stale fallback | Artifact identity differs from current Overview
D-01 | Decision | Priority | Choose Ngee acceptance before Coding Agent expansion | Protects the shortest route to customer proof | High | Sponsor | 2026-08-21 | Open | Recommend Ngee + A/B + feedback loop first | Coding Agent work starts before R2 exit
D-02 | Decision | Commercial packaging | Agree Pilot, Intelligence and Enterprise offer boundaries | Needed for customer proposal and pricing | Medium | Product + Sales | 2026-09-04 | Open | Validate packaging with Charles and Ngee feedback | Customer proposal requested without scope
D-03 | Decision | Ownership | Name Product, Energy, QA/UAT and Operations owners | Without owners dates remain indicative | High | Sponsor | 2026-08-21 | Open | Publish RACI for R1-R2 | A gate has no sign-off owner
A-01 | Assumption | Timeline | The 90-day sequence assumes current team capacity continues | Dates move if acceptance or data access is delayed | Medium | PMO | 2026-08-21 | Open | Rebaseline after R1 | Capacity or customer access changes

## 08_Evidence_Register
Evidence & Acceptance Register | Evidence & Acceptance Register | Evidence & Acceptance Register | Evidence & Acceptance Register | Evidence & Acceptance Register | Evidence & Acceptance Register | Evidence & Acceptance Register
A claim is not Done until its engineering, deployment and human-acceptance level is explicit | A claim is not Done until its engineering, deployment and human-acceptance level is explicit | A claim is not Done until its engineering, deployment and human-acceptance level is explicit | A claim is not Done until its engineering, deployment and human-acceptance level is explicit | A claim is not Done until its engineering, deployment and human-acceptance level is explicit | A claim is not Done until its engineering, deployment and human-acceptance level is explicit | A claim is not Done until its engineering, deployment and human-acceptance level is explicit
ID | Evidence type | Reference | What it supports | As of | Evidence level | URL / Path
EV-001 | Repository baseline | main@7070843 | Current integration line used for this roadmap draft | 2026-08-17 | Engineering | D:/Projects/energyiq-datafoundry-demo-integration
EV-002 | GitHub issue | #60 closed | Preschool real Snapshot A/B engineering acceptance | 2026-08-17 | Engineering | https://github.com/Zion74/energyiq-datafoundry/issues/60
EV-003 | GitHub issue | #58 closed | Additional Insight Provider pass@3 and value boundary | 2026-08-15 | Engineering | https://github.com/Zion74/energyiq-datafoundry/issues/58
EV-004 | GitHub issue | #59 closed | Approved Additional candidate publication to current Overview | 2026-08-15 | Engineering | https://github.com/Zion74/energyiq-datafoundry/issues/59
EV-005 | GitHub issue | #53 open | Multi-account and project-boundary human acceptance | 2026-08-17 | Human acceptance pending | https://github.com/Zion74/energyiq-datafoundry/issues/53
EV-006 | GitHub issue | #55 open | Ngee server-persisted Layer 1-3 Adapter | 2026-08-17 | Implementation / acceptance | https://github.com/Zion74/energyiq-datafoundry/issues/55
EV-007 | GitHub issue | #56 open | Ngee Snapshot A/B value acceptance | 2026-08-17 | Planned | https://github.com/Zion74/energyiq-datafoundry/issues/56
EV-008 | GitHub issue | #57 open | Insight usefulness to Method/SOP feedback loop | 2026-08-17 | Planned | https://github.com/Zion74/energyiq-datafoundry/issues/57
EV-009 | GitHub map | #62 open | Admin Harness Configuration and AI Operations roadmap | 2026-08-17 | In validation / planned | https://github.com/Zion74/energyiq-datafoundry/issues/62
EV-010 | Decision document | Overview AI decision | Layer 1-3, A/B, Evidence and Artifact product boundary | 2026-08-16 | Accepted design | docs/energyiq/2026-08-05-Overview用户价值与AI-Slot最小交付决策.md

## 09_Gantt
EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026 | EnergyIQ Detailed Delivery Gantt · Aug–Nov 2026
Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm | Execution view linked to the Delivery Plan · weekly bars are calculated from Start and Due dates · dates remain indicative until owners confirm
HOW TO READ · left side = accountable delivery data · right side = weekly execution window · bars update when Start / Due dates change in 02_Delivery_Plan
ID | Workstream | Deliverable | Owner | Status | % | Start | Due | Dependency | Acceptance / Exit Gate | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09
DLV-001 | Verified Foundation | Lock Snapshot, Evidence and project-scoped identity | Platform | Engineering Verified | 100% | 2026-08-03 | 2026-08-07 |  | Exact identity tests and persisted Evidence | bar: 2026-08-03
DLV-002 | Verified Foundation | Deliver Ngee Ann deterministic Overview | Product + Data | Engineering Verified | 100% | 2026-08-03 | 2026-08-10 | DLV-001 | Golden data, hierarchy and decision-page evidence | bar: 2026-08-03 to 2026-08-10
DLV-003 | Verified Foundation | Deliver Preschool deterministic decision Overview | Product + Data | Engineering Verified | 100% | 2026-08-06 | 2026-08-12 | DLV-001 | Benchmark and operating sections accepted in engineering | bar: 2026-08-03 to 2026-08-10
DLV-004 | Verified Foundation | Connect trusted AI Analyst and Saved Analysis | AI Platform | Engineering Verified | 100% | 2026-08-03 | 2026-08-07 | DLV-001 | Scoped queries, Evidence and restore tests | bar: 2026-08-03
DLV-005 | Verified Foundation | Complete Preschool A to B engineering acceptance | Product + AI | Engineering Verified | 100% | 2026-08-14 | 2026-08-17 | DLV-003;DLV-004 | Overview and AI domain change; stale Artifact rejected | bar: 2026-08-10 to 2026-08-17
DLV-101 | Acceptance Hardening | Human-review Preschool Key Findings | Product | Acceptance Pending | 90% | 2026-08-17 | 2026-08-21 | DLV-003 | Boss can identify top conclusions in 20 seconds | bar: 2026-08-17
DLV-102 | Acceptance Hardening | Human-review every Preschool Section Insight | Product + Energy | Acceptance Pending | 90% | 2026-08-17 | 2026-08-24 | DLV-003 | Summary is direct; Insights add a worthwhile angle | bar: 2026-08-17 to 2026-08-24
DLV-103 | Acceptance Hardening | Approve and publish useful Additional Insights | Energy + AI | Acceptance Pending | 90% | 2026-08-17 | 2026-08-24 | DLV-004 | Fact, inference and speculation remain honestly separated | bar: 2026-08-17 to 2026-08-24
DLV-104 | Acceptance Hardening | Run Charles and Ngee multi-account browser acceptance | QA + Ops | Acceptance Pending | 70% | 2026-08-17 | 2026-08-24 | DLV-002;DLV-003 | Admin sees all; Ngee account sees Ngee only; AI works | bar: 2026-08-17 to 2026-08-24
DLV-105 | Acceptance Hardening | Accept Admin AI Operations and Finding trace | Admin Product | Acceptance Pending | 70% | 2026-08-17 | 2026-08-28 | CAP-09 | Available vs used is clear; no GET triggers Provider | bar: 2026-08-17 to 2026-08-24
DLV-106 | Acceptance Hardening | Publish pilot runbook and rollback evidence | Ops | In Progress | 55% | 2026-08-20 | 2026-08-28 | DLV-104 | Health, backup, rollback and account runbook accepted | bar: 2026-08-17 to 2026-08-24
DLV-201 | Cross-project AI | Close Ngee Ann server-persisted Layer 1-3 Adapter | AI Platform | In Progress | 85% | 2026-08-15 | 2026-08-28 | DLV-002;DLV-004 | Saved/live restore exact; normal page open starts zero Provider runs | bar: 2026-08-10 to 2026-08-24
DLV-202 | Cross-project AI | Run real Ngee Ann Snapshot A to B | Product + AI | Planned | 15% | 2026-08-31 | 2026-09-11 | DLV-201 | Retained, updated, new and removed conclusions are visible | bar: 2026-08-31 to 2026-09-07
DLV-203 | Cross-project AI | Document common adapter and project-specific pack boundary | Architecture | Planned | 20% | 2026-09-07 | 2026-09-18 | DLV-201;DLV-202 | A third project can implement the contract without copying sections | bar: 2026-09-07 to 2026-09-14
DLV-301 | Learning Loop | Capture usefulness, novelty, clarity and Explore events | Product Analytics | Planned | 10% | 2026-09-21 | 2026-10-02 | DLV-102;DLV-202 | Feedback is project/snapshot/finding scoped | bar: 2026-09-21 to 2026-09-28
DLV-302 | Learning Loop | Create Insight-to-Method proposal flow | Energy + Admin | Planned | 10% | 2026-09-28 | 2026-10-09 | DLV-301 | User-approved Insight can become a reviewable Method proposal | bar: 2026-09-28 to 2026-10-05
DLV-303 | Learning Loop | Version governed Harness policy | AI Platform | Planned | 10% | 2026-09-28 | 2026-10-09 | DLV-105 | Policy revisions are attributable and recoverable | bar: 2026-09-28 to 2026-10-05
DLV-401 | Pilot Scale | Prototype AI Template Proposal, Diff and Preview | Admin Product | Planned | 20% | 2026-10-12 | 2026-10-23 | DLV-203;DLV-303 | AI proposes; human reviews; publish remains explicit | bar: 2026-10-12 to 2026-10-19
DLV-402 | Pilot Scale | Prototype controlled visual Insight canvas | Frontend + AI | Planned | 10% | 2026-10-19 | 2026-10-30 | DLV-301 | Charts appear only when they improve understanding | bar: 2026-10-19 to 2026-10-26
DLV-403 | Pilot Scale | Run isolated Coding Agent architecture spike | Architecture | Discovery | 5% | 2026-10-19 | 2026-11-06 | DLV-203;DLV-303 | One user request becomes a reviewable, rerunnable proposal | bar: 2026-10-19 to 2026-11-02
DLV-404 | Pilot Scale | Complete customer handover and commercial pilot review | Product + Sales | Planned | 10% | 2026-11-02 | 2026-11-06 | DLV-104;DLV-202;DLV-302 | Usage, value, support and next-phase decisions are signed | bar: 2026-11-02